## Gantt Chart
🐾 PawStay — Project Chronogram
Pet Hotel Booking Marketplace ¦ Solo Developer ¦ 14 Weeks ¦ Next.js + Supabase + Stripe
[6 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 | Sprint 7
Sprint | Task | Est. Hours | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
Sprint 1 Foundation & Auth | 1.1 — Project Initialization | 8 | bar: W1
| 1.2 — Supabase DB Schema Setup | 12 | bar: W1 to Sprint 6 W14
| 1.3 — Authentication UI & Logic | 16 | bar: W1 to W2
| 1.4 — Navigation & Layouts | 10 | bar: W1 to Sprint 6 W14
Sprint 2 Operator Features | 2.1 — Operator Onboarding Wizard | 20 | bar: W3
| 2.2 — Hotel Listing Editor | 18 | bar: W1 to Sprint 6 W14
| 2.3 — Operator Dashboard Overview | 12 | bar: Sprint 1 W4
Sprint 3 Search & Discovery | 3.1 — Search Page | 20 | bar: W1 to Sprint 6 W14
| 3.2 — Hotel Detail Page | 18 | bar: Sprint 1 W5 to Sprint 2 W6
| 3.3 — Pet Profiles Management | 12 | bar: W1 to Sprint 6 W14
Sprint 4 Booking & Payments | 4.1 — Booking Flow UI | 20 | bar: Sprint 2 W7
| 4.2 — Stripe Integration | 20 | bar: W1 to Sprint 6 W14
| 4.3 — Booking Management (Owner) | 14 | bar: Sprint 3 W8
Sprint 5 Reviews & Messaging | 5.1 — Reviews System | 16 | bar: W1 to Sprint 6 W14
| 5.2 — In-App Messaging (Realtime) | 20 | bar: Sprint 3 W9 to Sprint 4 W10
Sprint 6 Dashboards & Admin | 6.1 — Operator Bookings & Calendar | 18 | bar: W1 to Sprint 6 W14
| 6.2 — Operator Revenue & Settings | 12 | bar: Sprint 4 W11 to Sprint 5 W12
| 6.3 — Admin Panel | 20 | bar: W1 to Sprint 6 W14
Sprint 7 Polish & Launch | 7.1 — Favorites Feature | 8 | bar: Sprint 5 W13
| 7.2 — SEO & Performance | 12 | bar: W1 to Sprint 6 W14
| 7.3 — Email Templates | 14 | bar: Sprint 5 W13 to Sprint 6 W14
| 7.4 — Error Handling & Final QA | 16 | bar: W1 to Sprint 6 W14
TOTAL ESTIMATED HOURS |  | 336
Legend
Sprint 1: Foundation & Auth
Sprint 2: Operator Features
Sprint 3: Search & Discovery
Sprint 4: Booking & Payments
Sprint 5: Reviews & Messaging
Sprint 6: Dashboards & Admin
Sprint 7: Polish & Launch

## Sprint Overview
🐾 PawStay — Sprint Overview
Sprint | Focus | Weeks | Est. Hours | Tasks | Key Deliverables
Sprint 1 | Foundation & Auth | 1–2 | 46 hrs | 4 tasks | Project scaffold, Supabase DB, Auth flows, Navigation/Layouts
Sprint 2 | Operator Features | 3–4 | 50 hrs | 3 tasks | Operator onboarding wizard, Listing editor, Operator dashboard
Sprint 3 | Search & Discovery | 5–6 | 50 hrs | 3 tasks | Search page with maps & filters, Hotel detail page, Pet profiles
Sprint 4 | Booking & Payments | 7–8 | 54 hrs | 3 tasks | 3-step booking flow, Stripe Checkout + Connect, Owner booking mgmt
Sprint 5 | Reviews & Messaging | 9–10 | 36 hrs | 2 tasks | Star rating reviews, Operator replies, Real-time Supabase chat
Sprint 6 | Dashboards & Admin | 11–12 | 50 hrs | 3 tasks | Operator calendar, Revenue tracking, Admin panel
Sprint 7 | Polish & Launch | 13–14 | 50 hrs | 4 tasks | Favorites, SEO/perf, Email templates, QA & launch
TOTAL |  | 14 Weeks | 336 hrs | 22 tasks | ~24 hrs/week average for solo developer

## Task Details
🐾 PawStay — Detailed Task List
Feed each task row to your AI coding agent as a self-contained prompt
Task ID | Sprint | Task Name | Est. Hours | Weeks | Priority | Key Output / Agent Prompt Summary
1.1 | Sprint 1 | Project Initialization | 8 | 1 | High | Next.js 15 scaffold, env vars, folder structure, all dependencies
1.2 | Sprint 1 | Supabase DB Schema Setup | 12 | 1 | High | Full SQL schema + RLS policies + triggers + seed data
1.3 | Sprint 1 | Authentication UI & Logic | 16 | 1–2 | High | Signup/login/logout, Google OAuth, role-based onboarding flow
1.4 | Sprint 1 | Navigation & Layouts | 10 | 2 | High | Header, footer, owner/operator sidebar layouts, homepage
2.1 | Sprint 2 | Operator Onboarding Wizard | 20 | 3 | High | 5-step wizard: details, services, pets, photos, pricing
2.2 | Sprint 2 | Hotel Listing Editor | 18 | 3–4 | High | 6-tab editor: info, services, photos, pets/amenities, calendar, policies
2.3 | Sprint 2 | Operator Dashboard Overview | 12 | 4 | Med | Stats cards, upcoming bookings list, revenue bar chart
3.1 | Sprint 3 | Search Page | 20 | 5 | High | Location + date + pet + service search, filters, map toggle, pagination
3.2 | Sprint 3 | Hotel Detail Page | 18 | 5–6 | High | Gallery, services, availability calendar, reviews, booking CTA
3.3 | Sprint 3 | Pet Profiles Management | 12 | 6 | High | Pet CRUD with photo/doc uploads, species picker
4.1 | Sprint 4 | Booking Flow UI | 20 | 7 | High | 3-step: select service/dates/pets → review → payment → confirmation
4.2 | Sprint 4 | Stripe Integration | 20 | 7–8 | High | Checkout Sessions, Connect, webhooks, booking creation on payment
4.3 | Sprint 4 | Booking Management (Owner) | 14 | 8 | High | Upcoming/past/cancelled tabs, cancel with Stripe refund
5.1 | Sprint 5 | Reviews System | 16 | 9 | Med | Post-stay review form, star ratings, operator reply, moderation
5.2 | Sprint 5 | In-App Messaging (Realtime) | 20 | 9–10 | Med | Conversation list, chat UI, Supabase Realtime, email notifications
6.1 | Sprint 6 | Operator Bookings & Calendar | 18 | 11 | Med | Bookings list with actions, month/week calendar view with blocking
6.2 | Sprint 6 | Operator Revenue & Settings | 12 | 11–12 | Med | Revenue charts, Stripe Connect settings, notification preferences
6.3 | Sprint 6 | Admin Panel | 20 | 12 | Med | Platform metrics, listing approval queue, user management
7.1 | Sprint 7 | Favorites Feature | 8 | 13 | Low | Heart button, favorites page, optimistic UI, toggleFavorite action
7.2 | Sprint 7 | SEO & Performance | 12 | 13–14 | High | Metadata, JSON-LD, sitemap, OG images, Lighthouse ≥ 90
7.3 | Sprint 7 | Email Templates | 14 | 13–14 | Med | 7 React Email templates, Resend integration, preview server
7.4 | Sprint 7 | Error Handling & Final QA | 16 | 14 | High | Error boundaries, security audit, a11y fixes, production checklist